## Gantt Chart
MaisonQuest - Project Gantt chart & Delivery Roadmap
Project start: 01 Mar 2026 ¦ Platform: MaisonQuest (Cameroon Real Estate Marketplace) ¦ Owner: Mel-smith Koge ¦ Status: Active Testing
| Task / Delivrables | Phase | Owner | Start Date | End Date | Duration | Status | Priority | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27
PHASE 0 - INITIATION & DISCOVERY
| Define Project vision & Scope | Initiation | Founder | 2026-03-01 | 2026-03-07 | 1 week | Complete | High
| Identify target users & stakeholders | intiation | Founder | 2026-03-01 | 2026-03-07 | 1 Week | Complete | High
| Research Cameroonian real-estate market | initiation | Founder | 2026-03-01 | 2026-03-07 | 1 Week | Complete | High
| Decide the platform model (B2B2C) | initiation | Founder | 2026-03-08 | 2026-03-15 | 1 week | Complete | High
| Choose platform name - MaisonQuest | initiation | Founder | 2026-03-08 | 2026-03-15 | 1 week | Complete | Medium
| Register Business | initiation | Founder | 2026-03-15 | 2026-08-08 | 4 months | In Progress | High
PHASE 1 - PLANNING & DESIGN
| Define feature requirements | Planning | Founder | 2026-03-15 | 2026-03-22 | 1 week | Complete | High
| Map user journeys (renter & agency) | Planning | Founder | 2026-03-15 | 2026-03-22 | 1 week | Complete | High
| Choose tech stack | Planning | Founder/Claude | 2026-03-15 | 2026-03-15 | 1 week | Complete | High
| Define monetisation model | Planning | Founder | 2026-03-15 | 2026-03-15 | 1 week | Complete | Medium
| Design colour & branding system | Planning | Founder/Claude | 2026-03-22 | 2026-03-29 | 1 week | Complete | Medium
| Plan bilingual strategy (EN/FR) | Planning | Founder/Claude | 2026-03-22 | 2026-03-29 | 1 week | Complete | Medium
| Create project Gantt chart | Planning | Founder | 2026-03-29 | 2026-04-05 | 1 week | Complete | Medium
PHASE 2 - FRONTEND DEVELOPMENT
| Homepage (search, featured listings) | Execution | Claude | 2026-03-22 | 2026-03-29 | 1 week | Complete | High
| Listings / search results page | Execution | Claude | 2026-03-22 | 2026-03-29 | 1 week | Complete | High
| Listing detail page | Execution | Claude | 2026-03-29 | 2026-04-05 | 1 week | Complete | High
| Agency public profile page | Execution | Claude | 2026-03-29 | 2026-04-05 | 1 week | Complete | High
| Agency dashboard | Execution | Claude | 2026-03-29 | 2026-04-19 | 1 week | Complete | High
| Renter Dashboard | Execution | Claude | 2026-04-05 | 2026-04-19 | 1 week | Complete | High
| Authentication page (login/setup) | Execution | Claude | 2026-04-12 | 2026-04-19 | 1 week | Complete | High
| About & Contact pages | Execution | Claude | 2026-04-12 | 2026-04-19 | 1 week | Complete | Medium
| Cross-page navigation & deep links | Execution | Claude | 2026-04-12 | 2026-04-19 | 1 week | Complete | High
| Currency switcher (XAF/USD/EUR/GBP) | Execution | Claude | 2026-04-12 | 2026-04-19 | 1 week | Complete | Medium
| Full EN/FR translation system | Execution | Claude | 2026-03-29 | 2026-04-05 | 1 week | Complete | High
| Review system (like, flag, reply) | Execution | Claude | 2026-04-19 | 2026-04-26 | 1 week | Complete | High
| Analytics drilldown (click-to-expand months) | Execution | Claude | 2026-04-19 | 2026-04-26 | 1 week | Complete | High
| Session management (logout & login) | Execution | Claude | 2026-04-19 | 2026-04-26 | 1 week | Complete | High
| Deploy to Netlify (live URL) | Execution | Founder | 2026-04-26 | 2026-05-03 | 1 week | Complete | Medium
PHASE 3 - TESTING & QA
| Cross-browser testing (Chrome, Safari) | Testing | Founder | 2026-04-26 | 2026-05-03 | 1 week | Complete | High
| Mobile responsiveness review | Testing | Founder | 2026-04-26 | 2026-05-03 | 1 week | Complete | High
| Filter & Search QA | Testing | Founder | 2026-04-26 | 2026-05-03 | 1 week | Complete | High
| Auth flow end-to-end test | Testing | Founder | 2026-04-26 | 2026-05-03 | 1 week | Complete | High
| Review & flag feature testing | Testing | Founder | 2026-05-03 | 2026-05-10 | 1 week | Complete | Medium
| Translation accuracy review (FR) | Testing | Founder | 2026-05-03 | 2026-05-10 | 1 week | Complete | Medium
| Accessibility audit | Testing | Founder | 2026-05-03 | 2026-05-10 | 1 week | Complete | Low
PHASE 4 - BACKENED (SUPABASE)
| Set up Supbase project & enviroment | Execution | Founder/Claude | 2026-05-10 | 2026-05-17 | 1 week | In Progress | High
| Database schema design | Execution | Founder/Claude | 2026-05-10 | 2026-05-17 | 1 week | Not started | High
| Row Level Security (RLS) policies | Execution | Claude | 2026-05-10 | 2026-05-17 | 1 week | Not started | High
| Authentication (real signup/login) | Execution | Claude | 2026-05-17 | 2026-05-31 | 1 week | Not started | High
| Listing API (create/read/update/delete) | Execution | Claude | 2026-05-17 | 2026-05-31 | 1 week | Not started | High
| Imge storage (listing photos) | Execution | Claude | 2026-05-17 | 2026-05-31 | 1 week | Not started | High
| Inquiry & messaging system | Execution | Claude | 2026-05-24 | 2026-05-31 | 1 week | Not started | High
| Review & Ratings API | Execution | Claude | 2026-05-24 | 2026-05-31 | 1 week | Not started | Medium
| MTN Mobile Money integration | Execution | Founder/Claude | 2026-05-31 | 2026-06-07 | 1 week | Not started | High
| Search & filter API | Execution | Claude | 2026-06-07 | 2026-06-14 | 1 week | Not started | High
| Agency subscription tracking | Execution | Claude | 2026-06-07 | 2026-06-14 | 1 week | Not started | High
| GitHub Action CI/CD pipeline | Execution | Founder/Claude | 2026-06-14 | 2026-06-21 | 1 week | Not started | Medium
PHASE 5 - SOFT LAUNCH
| Onboard first 3-5 agency partners | Launch | Founder | 2026-06-21 | 2026-07-05 | 1 week | Not started | High
| Upload real listing content | Launch | Founder | 2026-06-21 | 2026-07-05 | 1 week | Not started | High
| Connect custom domain (maisonquest.com) | Launch | Founder | 2026-06-21 | 2026-06-28 | 1 week | Not started | High
| Announce on social media & WhatsApp | Launch | Founder | 2026-06-28 | 2026-07-05 | 1 week | Not started | High
| Gather early user feedback | Launch | Founder | 2026-06-28 | 2026-07-12 | 1 week | Not started | High
PHASE 6 - GROWTH & ITERATION
| Add more cities (Bafoussam, Buea, Limbe…) | Launch | Founder/Claude | 2026-07-12 | 2026-07-26 | 1 week | Not started | Medium
| SMS notification system | Launch | Claude | 2026-07-12 | 2026-07-26 | 1 week | Not started | Medium
| Android mobile app (PWA or React Native | Launch | Claude | 2026-07-26 | 2026-08-23 | 1 week | Not started | High
| Mortgage/financing referral partneships | Launch | Founder | 2026-08-09 | 2026-09-06 | 1 week | Not started | Low
| Help / FAQ page | Launch | Founder/Claude | 2026-07-12 | 2026-07-19 | 1 week | Not started | Low
LEGEND
Complete
Not starteted
In progress